## Sheet1
Date Started | Date Completed | Task | Description
28-07-2019 | 01-08-2019 | Requirement Gathering | Gathered information on Hotel management system by looking at the real world examples of how and what data is being managed by hotels
04-08-2019 | 08-08-2019 | Creating Tables | Worked on creating tables and constraints
09-08-2019 | 10-08-2019 | Reports | Worked on my individual breakdown on tables
10-08-2019 | 11-08-2019 | ER- Diagram | Worked closely with the group partner to create ER Diagram with all the relationships